## WBS
2018_WithTogether_5TS_WBS
WBS ID | ID Name |  | 작업책임자 | 계획일자 |  |  | 진행상태 |  | 실행일자 |  |  | 초과 | 2018년 10월 | [30 empty] | 2018년 11월
|  |  |  | 시작일 | 종료일 | 기간 |  |  | 시작일 | 종료일 | 기간 | [8 empty] | 월 | 화 | 수 | 목 | 금 |  |  | 월 | 화 | 수 | 목 | 금 |  |  | 월 | 화 | 수 | 목 | 금 |  |  | 월 | 화 | 수 | 목 | 금 |  | 월 | 화
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 | Project Management |  | 전체 | 2018-10-01 | 2018-11-05 | 26 |  |  | 2018-10-01 | 2018-11-05 | 26 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1 | 프로젝트 수행 준비 |  | 전체 | 2018-10-01 | 2018-10-11 | 9 | 100 | 완료 | 0 | 0 | 0 | 0
1.1.1 | 아이디어 구상 |  | 전체 | 2018-10-01 | 2018-10-08 | 6 | 100 | 완료 |  |  | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.2 | 화면설계서 구상 |  | 전체 | 2018-10-03 | 2018-10-11 | 7 | 100 | 완료 |  |  | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.3 | WorkFlow 구상 |  | 전체 | 2018-10-03 | 2018-10-08 | 4 | 100 | 완료 |  |  | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.4 | ERD설계 구상 |  | 전체 | 2018-10-03 | 2018-10-08 | 4 | 100 | 완료 |  |  | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.5 | 기능설명서 구상 |  | 전체 | 2018-10-03 | 2018-10-08 | 4 | 100 | 완료 |  |  | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.6 | WBS 작성 |  | 전체 | 2018-10-03 | 2018-10-08 | 4 | 100 | 완료 |  |  | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.2 | 프로젝트 Kick-Off |  | 전체 | 2018-10-10 | 2018-10-10 | 1 | 100 | 완료 | 2018-10-10 | 2018-10-10 | 1 | 0
1.2.1 | Kick-Off 일정 확정 |  | 전체 | 2018-10-10 | 2018-10-10 | 1 | 0 | 준비 | 2018-10-10 | 2018-10-10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3 | 전체 기능 분석및 설계 |  | 전체 | 2018-10-08 | 2018-10-10 | 3 | 0 | 준비 | 0 | 0 | 0 | 0
1.3.1 | 화면설계서 작성 |  | 전체 | 2018-10-08 | 2018-10-10 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.2 | WorkFlow 작성 |  | 전체 | 2018-10-08 | 2018-10-10 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.3 | ERD설계 작성 |  | 전체 | 2018-10-08 | 2018-10-10 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.4 | 기능설명서 작성 |  | 전체 | 2018-10-08 | 2018-10-10 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.5 | 분석/설계 확인 및 변경, 보완 |  | 전체 | 2018-10-08 | 2018-10-10 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4 | 개별 기술 연구 기간 |  | 전체 | 2018-10-10 | 2018-10-26 | 13 | 0 | 준비 | 0 | 0 | 0 | 0
1.4.1 | 블로그 |  | 김태훈 | 2018-10-10 | 2018-10-26 | 13 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4.2 | 카페 분석 |  | 김승환 | 2018-10-10 | 2018-10-26 | 13 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4.3 | 가구 매칭 |  | 김선종 | 2018-10-10 | 2018-10-26 | 13 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4.4 | 최저가 검색 |  | 박현준 | 2018-10-10 | 2018-10-26 | 13 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4.5 | 판매점 검색 |  | 고예린 | 2018-10-10 | 2018-10-26 | 13 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5 | 블로그 |  | 김태훈 | 2018-10-11 | 2018-10-26 | 12 | 0 | 준비 | 0 | 0 | 0 | 0
1.5.1 | 블로그 기본 기능 |  | 김태훈 |  |  |  |  | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.2 | DB 구성 | 글 쓰기, 수정, 삭제, 사진올리기 | 김태훈 | 2018-10-11 | 2018-10-11 | 1 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.3 | 글쓰기, 수정 | 리뷰, 대댓글 (세션처리 포함) | 김태훈 | 2018-10-12 | 2018-10-14 | 1 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.4 | 사진 올리기 | 좋아요, 블로그 전체 페이지 구성 | 김태훈 | 2018-10-15 | 2018-10-16 | 2 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.6 | 블로그 분석 |  | 김태훈 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.7 | 회원정보 분석 | 회원 정보 분석(성별, 연령대) , 시각화 | 김태훈 | 2018-10-16 | 2018-10-16 | 1 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.8 | 블로그 추천 | 블로그 추천 (같은 스타일 순, 인기순(좋아요多)) | 김태훈 | 2018-10-16 | 2018-10-18 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.9 | 랭킹 | 블로그 랭킹 ( 좋아요多순 ) | 김태훈 | 2018-10-19 | 2018-10-19 | 1 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.10 | 리뷰 분석 | 리뷰 분석 ( 형태소 분석 시각화) | 김태훈 | 2018-10-22 | 2018-10-26 | 5 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.6 | 카페 분석 |  | 김승환 | 2018-10-11 | 2018-10-26 | 12 | 0 | 준비 |  |  | 0 | 0
1.6.1 | 웹 기능 | 카페 리스트, 품목 세부사항 댓글 작성/수정/삭제, 시각화 | 김승환 | 2018-10-11 | 2018-10-13 | 2 | 0 | 준비 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.6.2 | 크롤링 | 네이버 쇼핑 크롤링(리뷰, 평점) 카페 크롤링(리뷰,url,이미지) | 김승환 | 2018-10-11 | 2018-10-15 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Machine Learning |  | 김승환 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.6.3 | 분석 | 리뷰 분석 및 모델 만들기 (feature - 리뷰, label - 평점) | 김승환 | 2018-10-15 | 2018-10-21 | 5 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.6.4 | 랭킹 | 카페 리뷰에 대한 평점 예측하고 랭킹 부여 (평점+조회수+좋아요) | 김승환 | 2018-10-21 | 2018-10-26 | 5 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7 | 가구 매칭 |  | 김선종 | 2018-10-11 | 2018-10-26 | 12 | 0 | 준비 |  |  | 0 | 0 | 32: #VALUE!; 33: #VALUE!; 34: #VALUE!; 35: #VALUE!; 36: #VALUE!
1.7.1 | 분석 |  | 김선종 |  |  |  |  | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.2 | 인테리어 수집 | 인테리어 사진을 저장 | 김선종 | 2018-10-11 | 2018-10-23 | 9 | 0 | 준비 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.3 | 이미지 분석 | 이미지 색 추출 모델 -> 검증 | 김선종 | 2018-10-11 | 2018-10-15 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.4 | 사진 업로드 | .jsp에서 구현 | 김선종 | 2018-10-15 | 2018-10-15 | 1 |  | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.5 | 이미지 불러오기 | 사진과 비슷한 색의 인테리어를 DB 불러오기 | 김선종 | 2018-10-16 | 2018-10-17 | 2 | 0 | 준비 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.6 | 리뷰 분석 | tf-idf 모델 만들고 검증 | 김선종 | 2018-10-18 | 2018-10-23 | 4 | 0 | 준비 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.7 | 키워드 검색 | 키워드로 검색 되는지 확인 |  | 2018-10-24 | 2018-10-25 | 2 | 0 | 준비 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.8 | 시각화 |  | 김선종 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.9 | 이미지 띄우기 | 이미지 표시하기 | 김선종 | 2018-10-26 | 2018-10-26 | 1 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.10 | 상품 띄우기 | 키워드와 일치하는 상품 띄우기 | 김선종 | 2018-10-26 | 2018-10-26 | 1 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8 | 최저가 검색 |  | 박현준 | 2018-10-11 | 2018-10-26 | 12 | 0 | 준비 |  |  | 0 | 0
1.8.1 | 입력 |  | 박현준 |  |  |  |  | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.2 | 상품 파악 | 구글 이미지검색 api | 박현준 | 2018-10-11 | 2018-10-12 | 2 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.3 | 상품명 입력 | <form> | 박현준 | 2018-10-11 | 2018-10-12 | 2 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.4 | 최저가 출력 |  | 박현준 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.5 | 최저가 습득 | 셀레니움으로 쇼핑몰 검색 | 박현준 | 2018-10-16 | 2018-10-17 | 2 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.6 | 웹 출력 | 디자인 틀에 맞춰서 출력하기 | 박현준 | 2018-10-18 | 2018-10-19 | 2 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.7 | 취향 분석 |  | 박현준 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.8 | 이미지 크롤링 | 네이버 쇼핑 카테고리별 이미지 | 박현준 | 2018-10-15 | 2018-10-22 | 6 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.9 | 모델 만들기 | 케라스로 카테고리 분류 모델 | 박현준 | 2018-10-23 | 2018-10-25 | 3 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.8.10 | 결과 표시 | 분류 결과를 최저가출력에 표시 | 박현준 | 2018-10-26 | 2018-10-26 | 1 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.9 | 판매점 검색 |  | 고예린 | 2018-10-11 | 2018-10-26 | 12 | 0 | 준비 |  |  | 0 | 0
1.9.1 | 회원관리, 지도, 크롤링, CSS |  | 고예린 |  |  |  |  | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 회원 관리 | 회원가입 / 프사 업로드, 취향선택 | 고예린 | 2018-10-11 | 2018-10-11 | 1 | 0 | 준비
|  | 로그인 , 로그아웃 | 고예린 | 2018-10-11 | 2018-10-11 | 1 | 0 | 준비
|  | 회원가입 완료 화면 | 고예린 | 2018-10-12 | 2018-10-12 | 1 | 0 | 준비
|  | 회원 정보 수정 , 프로필 수정 | 고예린 | 2018-10-12 | 2018-10-12 | 1 | 0 | 준비
| 크롤링 | 인테리어 관련 사이트 | 고예린 | 2018-10-15 | 2018-10-15 | 1 | 0 | 준비
| 지도 | 가구 판매점 검색 | 고예린 | 2018-10-16 | 2018-10-16 | 1 | 0 | 준비
|  | 최저가 판매점 위치 | 고예린 | 2018-10-17 | 2018-10-17 | 1 | 0 | 준비
1.9.2 |  | 쪽지 | 고예린 | 2018-10-18 | 2018-10-22 | 3 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.9.3 | Visual Studio | 메인페이지 css | 고예린 | 2018-10-23 | 2018-10-24 | 2 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.9.4 |  | 블로그 css | 고예린 | 2018-10-24 | 2018-10-24 | 1 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.9.5 |  | 카페분석 css | 고예린 | 2018-10-25 | 2018-10-25 | 1 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.9.6 |  | 가구매칭 css | 고예린 | 2018-10-25 | 2018-10-25 | 1 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.9.7 |  | 최저가 검색 css | 고예린 | 2018-10-26 | 2018-10-26 | 1 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 판매점 검색 css | 고예린 | 2018-10-26 | 2018-10-26 | 1 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
기간 = IF(NETWORKDAYS([계획일자],[종료일])=0,"",NETWORKDAYS([계획일자],[종료일]))
기간 = IF(NETWORKDAYS([실행일자],[종료일])=0,0,NETWORKDAYS([실행일자],[종료일]))
계획일자 = MIN([계획일자, row below]:E12)
계획일자 = MIN([계획일자, row below]:[계획일자, row below])
종료일 = MAX([종료일, row below]:F12)
종료일 = MAX([종료일, row below]:K12)
실행일자 = MIN([실행일자, row below]:J12)
실행일자 = MIN([실행일자, row below]:[실행일자, row below])

## WBS(수정)
2018_WithTogether_5TS_WBS
WBS ID | ID Name |  | 작업책임자 | 계획일자 |  |  | 진행상태 |  | 실행일자 |  |  | 초과 | 2018년 10월 | [30 empty] | 2018년 11월
|  |  |  | 시작일 | 종료일 | 기간 |  |  | 시작일 | 종료일 | 기간 | [8 empty] | 월 | 화 | 수 | 목 | 금 |  |  | 월 | 화 | 수 | 목 | 금 |  |  | 월 | 화 | 수 | 목 | 금 |  |  | 월 | 화 | 수 | 목 | 금 |  | 월 | 화
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 | Project Management |  | 전체 | 2018-10-01 | 2018-11-05 | 26 |  |  | 2018-10-01 | 2018-11-05 | 26 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1 | 프로젝트 수행 준비 |  | 전체 | 2018-10-01 | 2018-10-12 | 10 | 100 | 완료 | 2018-10-01 | 2018-10-12 | 10 | 0
1.1.1 | 아이디어 구상 |  | 전체 | 2018-10-01 | 2018-10-12 | 10 | 100 | 완료 | 2018-10-01 | 2018-10-12 | 10 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.2 | 화면설계서 구상 |  | 전체 | 2018-10-03 | 2018-10-12 | 8 | 100 | 완료 | 2018-10-03 | 2018-10-12 | 8 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.3 | WorkFlow 구상 |  | 전체 | 2018-10-03 | 2018-10-12 | 8 | 100 | 완료 | 2018-10-03 | 2018-10-12 | 8 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.4 | ERD설계 구상 |  | 전체 | 2018-10-03 | 2018-10-12 | 8 | 100 | 완료 | 2018-10-03 | 2018-10-12 | 8 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.5 | 기능설명서 구상 |  | 전체 | 2018-10-03 | 2018-10-12 | 8 | 100 | 완료 | 2018-10-03 | 2018-10-12 | 8 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.1.6 | WBS 작성 |  | 전체 | 2018-10-03 | 2018-10-12 | 8 | 100 | 완료 | 2018-10-03 | 2018-10-12 | 8 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.2 | 프로젝트 Kick-Off |  | 전체 | 2018-10-10 | 2018-10-10 | 1 | 100 | 완료 | 2018-10-10 | 2018-10-10 | 1 | 0
1.2.1 | Kick-Off 일정 확정 |  | 전체 | 2018-10-10 | 2018-10-10 | 1 | 0 | 준비 | 2018-10-10 | 2018-10-10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3 | 전체 기능 분석및 설계 |  | 전체 | 2018-10-08 | 2018-10-12 | 5 | 0 | 준비 | 0 | 0 | 0 | 0
1.3.1 | 화면설계서 작성 |  | 전체 | 2018-10-08 | 2018-10-12 | 5 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.2 | WorkFlow 작성 |  | 전체 | 2018-10-08 | 2018-10-12 | 5 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.3 | ERD설계 작성 |  | 전체 | 2018-10-08 | 2018-10-12 | 5 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.4 | 기능설명서 작성 |  | 전체 | 2018-10-08 | 2018-10-12 | 5 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.5 | 분석/설계 확인 및 변경, 보완 |  | 전체 | 2018-10-08 | 2018-10-12 | 5 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.3.6 | 분석 계획 세우기 (김승환, 김선종, 박현준) |  | 전체 | 2018-10-11 | 2018-10-12 | 2 | 0 | 준비 |  |  | 0 | 0
1.4 | 개별 기술 연구 기간 |  | 전체 | 2018-10-12 | 2018-10-26 | 11 | 0 | 준비 | 0 | 2018-10-19 | 30995 | #REF!
1.4.1 | 블로그 |  | 김태훈 | 2018-10-12 | 2018-10-26 | 11 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4.2 | 카페 분석 |  | 김승환 | 2018-10-12 | 2018-10-26 | 11 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4.3 | 가구 매칭 |  | 김선종 | 2018-10-12 | 2018-10-26 | 11 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4.4 | 최저가 검색 |  | 박현준 | 2018-10-12 | 2018-10-26 | 11 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.4.5 | 판매점 검색 |  | 고예린 | 2018-10-12 | 2018-10-26 | 11 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5 | 웹 개발 |  |  | 2018-10-12 | 2018-10-26 | 11 | 0 | 준비 | 0 | 2018-10-15 | 30991 | #REF!
1.5.1 | 블로그 | 글 쓰기, 수정, 삭제, 사진올리기 리뷰, 대댓글 (세션처리 포함) 좋아요, 블로그 전체 페이지 구성 | 김태훈 | 2018-10-12 | 2018-10-18 | 5 | 50 | 준비 | 2018-10-12 | 2018-10-18 | 5 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.5.2 | 카페 분석 | 카페 리스트, 품목 세부사항 댓글 작성/수정/삭제 | 김승환 | 2018-10-12 | 2018-10-15 | 2 | 50 | 준비 | 2018-10-12 | 2018-10-15 | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.5.4 | 회원 관리 | 회원가입 / 프사 업로드, 취향선택, 메인 페이지 로그인 , 로그아웃 회원가입 완료 화면 회원 정보 수정 , 프로필 수정 | 고예린 | 2018-10-12 | 2018-10-13 | 1 | 25 | 준비 | 2018-10-12 | 2018-10-19 | 6 | #REF!
1.5.5 | 가구 매칭 | 사진 업로드 색추출 결과 시각화 시각화된 그래프 클릭 후 해당 색 인테리어 결과 보여주기 인테리어 추천결과 사진확대 기능(마우스 on) 남는 시간에 | 김선종 | 2018-10-24 | 2018-10-26 | 3 | 0 | 준비 |  |  | 0 | 0
1.5.6 | 지도 | 가구 판매점 검색 | 고예린 | 2018-10-15 | 2018-10-15 | 1 | 25 | 준비 |  |  | 0 | 0
1.5.7 | 쪽지 | 쪽지 기능 | 고예린 | 남는 시간에 | 남는 시간에 |  | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.5.8 | 상품 파악 | 구글 이미지검색 api | 박현준 | 2018-10-13 | 2018-10-15 | 1 | 0 | 준비 |  |  | 0 | 0
1.5.9 | 최저가 습득 | 네이버 api 이용하여 최저가 리스트 확보 (확인 필요함) | 박현준 | 2018-10-16 | 2018-10-16 | 1 | 0 | 준비 |  |  | 0 | 0
1.6 | 크롤링 |  |  | 2018-10-12 | 2018-10-17 | 4 | 0 | 준비 | 0 | 2018-10-15 | 30991 | #REF!
1.6.1 | 네이버리뷰 수집 | 네이버 쇼핑 크롤링(리뷰, 평점) | 김승환 | 2018-10-12 | 2018-10-17 | 4 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1.6.2 | 카페리뷰 수집 | 카페 크롤링(리뷰,url,이미지) | 김승환 | 2018-10-12 | 2018-10-17 | 4 | 0 | 준비 |  |  | 0 | 0
1.6.3 | 인테리어 수집 | 인테리어 사진을 저장 | 김선종 | 2018-10-12 | 2018-10-17 | 4 | 50 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.6.4 | 가구 수집 | 네이버 쇼핑 가구 크롤링 ( 가구 카테고리별 분류 ) | 박현준 | 2018-10-12 | 2018-10-17 | 4 | 0 | 준비 |  |  | 0 | 0
1.7 | 분석 |  |  | 2018-10-12 | 2018-10-26 | 11 | 0 | 준비 | 0 | 2018-10-15 | 30991 | #REF! | 32: #VALUE!; 33: #VALUE!; 34: #VALUE!; 35: #VALUE!; 36: #VALUE!
1.7.1 | 회원정보 분석 | 회원 정보 분석(성별, 연령대) , 시각화 | 김태훈 | 2018-10-19 | 2018-10-19 | 1 | 0 | 준비 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1.7.2 | 블로그 추천 | 블로그 추천 (같은 스타일 순, 인기순(좋아요多)) | 김태훈 | 2018-10-22 | 2018-10-22 | 1 | 0 | 준비 |  |  | 0 | 0
1.7.3 | 랭킹 | 블로그 랭킹 ( 좋아요多순 ) | 김태훈 | 2018-10-23 | 2018-10-23 | 1 | 0 | 준비 |  |  | 0 | 0
1.7.4 | 리뷰 분석 | 리뷰 분석 ( 형태소 분석 시각화) | 김태훈 | 2018-10-24 | 2018-10-24 | 1 | 0 | 준비 |  |  | 0 | 0
1.7.5 | 분석 | 네이버쇼핑 리뷰 분석(tf-idf) tf-idf모델 만들기 feature - 네이버 쇼핑 리뷰 텍스트 label - 네이버 쇼핑 리뷰 평점 predict feature - 카페 별 가구 리뷰 텍스트 predict result - tf-idf 결과 평점 [1~5점 정수 형태] | 김승환 | 2018-10-15 | 2018-10-24 | 8 | 50 | 준비 |  |  | 0 | 0 | [36 empty] | 2018.10.12 | 데모 이미지( 약 7000장) 크롤링 만듦
1.7.6 | 랭킹 | (1.7.6 모델 이용) 카페 리뷰에 대한 평점 예측하고 랭킹 부여 (평점+조회수+좋아요) | 김승환 | 2018-10-25 | 2018-10-26 | 2 | 0 | 준비 |  |  | 0 | 0 | [36 empty] | 2018.10.15 | 데모 데이터를 사용해서 이미지 분류 모델 만듦
1.7.8 | 이미지 분석 | 이미지 전체 색 추출 -> 추출한 결과 중 가장 많은 비율을 차지하는 색의 이름을 분류해주는 모델 만들기 (feature - R,G,B , label - 색상) | 김선종 | 2018-10-12 | 2018-10-15 | 2 | 100 | 준비 | 2018-10-12 | 2018-10-15 | 2 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 1899-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2018.10.16 | 만들어진 모델 파이참으로 실행 및 스프링과 연동 등
1.7.9 | 가구 매칭 | 인테리어의 색을 분류 가구 업로드 시 색을 분류하여, 분류된 인테리어 색과 매칭 (먼저 조금 해보고 만족할만한 결과가 안 나오면, PCA, NMF, Tensorflow, PyTorch) | 김선종 | 2018-10-16 | 2018-10-23 | 6 | 50 | 준비 |  |  | 0 | 0 | [36 empty] | 2018.10.17 | 사진 업로드 후 모델을 통해 얻은 출력값에 해당하는 이미지들 불러옴
1.7.10 | 모델 만들기 | (WBS ID 1.6.4 사진)텐서플로우로 카테고리 분류 (최저가 검색을 위해 입력된 사진의 카테고리를 분류함) | 박현준 | 2018-10-17 | 2018-10-26 | 8 | 0 | 준비 |  |  | 0 | 0 | [36 empty] | 2018.10.18
1.9 | css |  |  | 2018-10-15 | 2018-10-26 | 10 | 0 | 준비 | 0 | 0 | 0 | 0
1.9.3 |  | 모든 페이지 | 고예린 | 2018-10-15 | 2018-10-26 | 10 | 0 | 준비 |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2.0.0 | 추가 개발
1.5.3 | 키워드 매칭 | 키워드로 가구 매칭 Word2Vec | 김승환 | 2018-10-16 | 2018-10-16 | 1 | 0 | 준비 |  |  | 0 | 0
1.7.7 | 키워드 매칭 | 분석 결과와 입력한 키워드를 매칭 | 김승환 | 2018-10-24 | 2018-10-26 | 3 | 0 | 준비 |  |  | 0 | 0
이웃
스크랩
Formulas:
기간 = IF(NETWORKDAYS([계획일자],[종료일])=0,"",NETWORKDAYS([계획일자],[종료일]))
기간 = IF(NETWORKDAYS([실행일자],[종료일])=0,0,NETWORKDAYS([실행일자],[종료일]))
계획일자 = MIN([계획일자, row below]:E12)
계획일자 = MIN([계획일자, row below]:[계획일자, row below])
종료일 = MAX([종료일, row below]:F12)
종료일 = MAX([종료일, row below]:K12)
실행일자 = MIN([실행일자, row below]:J12)
실행일자 = MIN([실행일자, row below]:[실행일자, row below])

## Sheet1
스프링 MVC를 활용한 개발 (오라클만 활용해도 개발 가능함)
로그인 | 조승현 | 2018-03-27 | 2018-04-03 | 한세희 | 2018-04-02 | 2018-04-06
회원가입 | 조승현 | 2018-03-27 | 2018-04-03 | 한세희 | 2018-04-02 | 2018-04-06
회원가입 완료 화면 | 조승현 | 2018-03-27 | 2018-04-03 | 한세희 | 2018-04-09 | 2018-04-12
MongoDB 및 딥 러닝 결과물을 활용한 클라이언트 개발
코스추천받기 | 조승현 | 2018-04-03 | 2018-04-06 | 한세희 | 2018-04-12 | 2018-04-16
지도 | 조승현 | 2018-04-06 | 2018-04-09 | 한세희 | 2018-04-16 | 2018-04-18
추천코스 | 조승현 | 2018-04-09 | 2018-04-12 | 한세희 | 2018-04-18 | 2018-04-20
My코스 | 조승현 | 2018-04-12 | 2018-04-15 | 한세희 | 2018-04-20 | 2018-04-24
날씨 | 조승현 | 2018-04-15 | 2018-04-18 | 한세희 | 2018-04-24 | 2018-04-26
Top10 | 조승현 | 2018-04-18 | 2018-04-21 | 한세희 | 2018-04-26 | 2018-04-30
SPA(Single Page Application)